## MainPage
Metric for Defect leakages
Author | Nagaraj B Mali | Seniro SDET Architect
Version | 1.4.1
Last Update | 2024-10-08

## Overall Metrics
Sprint Management
Backlogs
Stories Metrics
|  |  | 1) Definition of Ready (DoR) Checklist | DoR Checklist |  | Key Factors for Story Readiness
|  |  |  | Criteria | Status (Yes/No) | 1. Clearly Defined Scope | 2. Acceptance Criteria | 3. Dependencies Identified and Addressed | 4. Estimation Feasibility | 5. Prioritized | 6. Detailed Requirements | 7. Testability | 8. No Outstanding Questions | 9. Technical Feasibility | 10. Defined Success Criteria
|  |  | How Readiness Factors Impact Backlog Health | Scope Clarity: Story description is clear | ✅ Yes | The story must have a clear description of what needs to be done. | The story must include well-defined acceptance criteria that outline how the story will be validated. | All external and internal dependencies must be identified and resolved or have a clear plan for resolution. | The story must be small enough to estimate accurately and deliver within a sprint. | The story must align with business priorities and have approval for inclusion in the sprint. | The story must have all necessary details and inputs for implementation and testing. | The story must be testable, with clear conditions for validation. | All team members should have a shared understanding of the story. | The technical aspects of the story should be understood and feasible. | The story must have clear success criteria that align with the expected outcome.
|  |  | --> Improves Predictability: Ensures that the team can confidently estimate and deliver stories within a sprint. | Acceptance criteria are defined | ✅ Yes | What to Check: | What to Check: | What to Check: | What to Check: | What to Check: | What to Check: | What to Check: | What to Check: | What to Check: | What to Check:
|  |  | --> Reduces Risk: Minimizes last-minute surprises or blockers during implementation. | Dependencies are identified | ✅ Yes | Does the story have a concise and unambiguous description? | Are the acceptance criteria clear, testable, and exhaustive? | Are there any dependencies on other teams, systems, or stories? | Is the story appropriately sized for a sprint? (Typically 1–3 days of work for development and testing.) | Is the story aligned with the sprint's goals or broader project milestones? | Are functional and non-functional requirements clearly stated? | Can test cases be created from the story and acceptance criteria? | Have all clarifications been addressed in grooming sessions? | Are there no unresolved technical unknowns? | Are the goals and success metrics for the story explicitly mentioned?
|  |  | --> Increases Efficiency: Saves time in sprint planning by ensuring all stories are ready to pick. | Story is small and estimable | ✅ Yes | Are the boundaries and scope well-defined, avoiding scope creep? | Do they cover both positive and negative scenarios? | Are blockers documented and tracked? | Has the story been broken down into smaller parts if too large? | Has it been prioritized correctly by the Product Owner? | Is additional documentation (e.g., wireframes, mockups, diagrams) attached if needed? | Are any specific tools or environments required for testing mentioned? | Are open questions resolved or documented? | Have architectural or system design aspects been considered and validated?
|  |  | --> Enhances Quality: Leads to better test coverage and fewer defects due to well-defined requirements and acceptance criteria. | Requirements are complete | ✅ Yes |  | Are edge cases considered?
|  |  |  | Testability is ensured | ✅ Yes
|  |  |  | No unresolved questions | ✅ Yes
|  |  |  | Technical feasibility is confirmed | ✅ Yes
|  |  |  | Prioritized and approved | ✅ Yes
|  |  |  | Success criteria are defined | ✅ Yes
How to use:
Mark each story its readiness [i.e Yes or No] Count no of readiness points against each Story.
QA should accept a story marked 10/10. Do not accept anything that is less than 100%
Define Complexity Metrics Set quantifiable metrics for feature complexity: A) Functional Complexity Measurement Criteria: 1) Count the number of functional paths (primary and alternate). 2) Number of integrations and APIs involved. 3) UI elements or interactions required. Example: Login feature: Low complexity. Multi-factor authentication: High complexity. B. Non-Functional Complexity Measurement Criteria: 1) Performance expectations (e.g., response time, scalability). 2) Security requirements. 3) Regulatory compliance. C. Data Complexity Measurement Criteria: 1) Number of input fields and data types. 2) Validation rules (e.g., required fields, regex patterns). 3) Data dependencies (e.g., pre-populated values). D. Dependency Complexity Measurement Criteria: 1) Interaction with third-party systems or external APIs. 2) Sequential dependencies on other features/modules.
2) Too Many High Priority stories cramped in 1 sprint
|  |  |  | QA's Testing Story Points |  | Key Factors for Story Readiness
After carefully analyzing the Readiess of each story, assign story points for Testing
|  |  |  | Analyze the 1) Interdependency between stories 2) interdependency between defect & stories 3) Independent Story 4) Independent Defect. | Story Points 1) Highest 2) High 3) Medium 4) Low | 1) Analyse Readiness 2) Assign % of test coverages exists 3) Factorize the coverages to Story Points and reCalibrate story points. Example.... A Story with 1) High Story point with zero test coverage becomes Highest Story Point 2) Low story point with zero test coverage becomes Medium Story Point 3) Medium story point with less than 50% coverage can become High Story Point | Coverage Percentage= ( Number of Identified Scenarios / Number of Test Cases Written ) × 100
|  |  | How to use: |  |  | Another way to assign story points
|  |  | Analyze and understand the impact of each story. [ Based on Collaborate [3 amigo], KTs and reverse KTs ] |  |  | Align testing depth and techniques with the feature's complexity score. High complexity → Comprehensive tests, automation, performance & security testing. Medium complexity → Focused functional and integration testing. Low complexity → Basic functional and smoke testing.
More the dependency or Number of business rules or Number of input/output combinations more is regression prone, more is the story point.
Always encourage for spill-overs for Testing efforts.
3) KT Evaluation Metrics
Combine key metrics into a dashboard for tracking over time:
Requirement-to-Test Case Coverage Ratio.
Percentage of defects traced to KT issues.
QA confidence rating post-KT (from surveys).
Average follow-up questions per KT session.
Number of gaps identified in test reviews due to insufficient KT.
How to use:
1) During KT, try to map the requirement with all notedcoveages, Add any missing scenarios, expand the collaboration.
2) Write test cases for all coverages and extra [BVA, EqP, Edge cases, integration cases, non-functional cases, cross-platform cases etc etc
3) If test cases already exist, enahnce then w.r.t KT & coverages mentioned.
4) Give QA confidence rating post KT- Track Continous improvments
5) In every Sprint Retrospective, give % of defects traced to KT issues/coverages missing. Very important metric. Keep it handy all the time.
I. Thorough Testing (High Impact, Low Risk) Examples: Key features that are stable or frequently used. Testing Focus: Comprehensive functional testing. Cover edge cases and boundary conditions. Include non-functional testing (e.g., performance, usability). Approach: Balance manual and automated testing for regression and exploratory scenarios. II. Focused Testing (High Impact, High Risk) Examples: Core functionalities undergoing significant changes or integration points. Testing Focus: Exhaustive functional and regression testing. Early and frequent testing during development. Include end-to-end and integration tests. Approach: Prioritize this quadrant with maximum effort to avoid critical defect leakage. III. Minimal Testing (Low Impact, Low Risk) Examples: Minor features, cosmetic changes, or components with no recent changes. Testing Focus: Smoke testing to ensure basic functionality. Skip exhaustive test cases unless required. Approach: Use automation or exploratory testing to save time. IV. Targeted Testing (Low Impact, High Risk) Examples: Features with a history of defects or technically complex but less critical. Testing Focus: Test only high-priority scenarios or risky areas. Limit testing effort to known weak points or integration paths. Approach: Automate repetitive tasks and focus on error-prone areas.
|  | Defect Metrics | 4) Risk Impact Matrix
|  |  | Cluster of Defects/Features testing completeness based on Risk-Impact matrix. 1 time activity. | Divide the matrix into four quadrants to guide test effort allocation:
|  |  |  | Risk → | Low Risk | High Risk
Impact ↓
|  |  |  | High Impact | Thorough Testing (I) | Focused Testing (II)
|  |  |  | Low Impact | Minimal Testing (III) | Targeted Testing (IV)
How to use:
1) Go through all the PROD defects, add labels to each.
2) Create metrics of feature vs no of defects
3) Mark high defects areas as Risks, mark high business impact defect areas/features as High Risk
4) Create Risk vs Impact matrix. Its one time activity
5) Decide Testing Completeness based on this matrix.
*** People also use feature to feature dependency vs number of scenarios to calculate testing effort
TestCase Metrics
5) Test Case Effectiveness
Indicates how many defects were detected by executed test cases.
Effectiveness = Defects Found in Testing / Total Defects (Including Production)​ × 100
How to Usage:
A low effectiveness score suggests missed scenarios or weak test cases.
Correlate ineffective test cases with production defects to identify gaps.
6) Test Case Failure Rate
Definition: The percentage of test cases that failed during execution.
Failure Rate = Failed Test Cases / Executed Test Cases ​ × 100
How to Usage:
High failure rates in certain modules may correlate with production defects in those areas.
Analyze which types of failures (functional, performance, etc.) lead to production issues.
7) Defect Leakage Rate
|  |  | Definition: Percentage of defects that were missed during testing and found in production. | Defect Leakage Rate = Defects Found in Production​ / Total Defects ×100
How to Usage:
Use leakage trends to determine if specific test cases or areas need improvement.
A high leakage rate indicates poor alignment of test cases with risk-prone areas.
Sprint Testing

## Sprint Metrics for QAs
Sprint iterations......
| January | February | March | April | May | June | July | August | September
No Of Planned 2 weeks sprints | 2 | 2
Parallel sprints | 3 | 3
Actual sprints per month | 6 | 6
No Of Complex features considered | 3 | 5
No Of P0 /P1 defects fixed | 8 | 12
No of KTs given based on complexity | 4 | 4
No of new coverages found by QAs | 16 | 16
No Of Developers worked | 12 | 12
No Of Point release | 4 | 4
No Of Hotfixes | 2 | 2
No Of Patches | 2 | 2
Total No Of releases | 6 | 6
No Of Planned QA resources | 4 | 4
No of planned testing days per sprint | 4 | 4
Actual number of testing days burned | 24 | 24
Per QA person days for testing | 6 | 6
No Of extra QAs added in-sprint | 2 | 4
% of extra QAs needed | 50% | 100%
Acceptance Criteria given/signed/agreed | Yes | Yes
Post Release
No Of defects found | 25 | 38
No Of defects leaked to PROD | 12 | 16
No Of Defects outside the coverage | 8 | 11
% of defects outside the coverage | 66.67% | 68.75%
Effectiveness of coverage | 33.33% | 31.25%
Cascading defects post above defect fix | 3 | 3
% Of defects fixed, caused cascading defects | 37.5% | 25%
Find many more co-relations between above parameters

## Sprint slippage-Holy grail is a
Key reasons why a feature might not be completed within the planned sprints:
Poorly defined user stories: | Unrealistic estimations: | Scope creep: | Lack of communication: | Technical challenges: | Inadequate backlog refinement: | Team dynamics:
Unclear requirements or user stories can lead to confusion and misinterpretations during development, causing delays and rework. | Overestimating the team's capacity or underestimating the complexity of tasks can result in a sprint backlog that is too ambitious to complete within the timeframe. | Changes in requirements or adding new features mid-sprint can significantly impact the planned work and lead to missed deadlines. | Poor communication between the product owner, development team, and stakeholders can lead to misunderstandings and delays. | Unexpected technical issues or dependencies on external systems can significantly slow down development. | Not properly breaking down large features into smaller, manageable user stories before sprint planning can lead to difficulties in estimation and execution. | Poor team collaboration, low morale, or lack of trust within the team can negatively impact productivity and sprint outcomes.
How to tap this as a QA manager
What to do if a feature is failing to meet its sprint plan: |  | Role Of QA Manager
Hold a sprint retrospective: |  | Analyze | Find cause | Proposes solution | Experiment | Finalize
| Analyze what went wrong in the current sprint to identify areas for improvement and adjust future planning accordingly. | 1) Analyse any delay from QAs to complete testing on time. Find the cause for this. | 1) Lack of enough QA resources 2) Technical debt 3) Complex feature 4) Lack of enough coverages 5) Integration issue 6) Sqeezed testing window. 7) Frequent distractions or frequent dev requests for early testing 8) Frequent meetings 9) Lack of KTs from PO or BA 10) No 3 amigos etc | 1) Find the diff in planned vs actual resources needed. ReCalibrate the resource requirement model based on complexity or other factors. 2) Technical debt: Check if QAs have Domain/feature/integrated system knwoledge. If not check if they are under training. Check if they received enough KTs, addressed their domain issues, caluclated their confidence on feature and integrations etc. 3) Measure the complexity. Check the QAs need to handle this feature. 4) Coverages: Check existing tests vs defects leaked. Coverage should be on-going activity. 5) Lack of integration coverages are deadly ones, they result in sprint slippages. Propose how to have enough integration coverages in tests. 6) If story-points for features are not enough. Experiment adding more resources by moving less loaded resource across. Always have resources capacity in place. 7) Frequent testing ask by Dev is a good sign. Encourage this. Dont stop this kind of activities. Find alternative solution for distractions. 8) Frequent meetings. Give liberty to QAs to skip such meeting during testing cycle. 9) KTs: Record, Document and maintain all feature related documents. Implement a culture of On-Priority domain/support from BA/PO/DEVs. 10) Encourage frequent 3 amigos meeting on feature health-checks. | Derive all the metrics out of these measures and tune the process
|  |  |  | QA should be given all KTs/Docs/help needed even before backlog refinement. So that QA will also have their say in managing the feature development/design/deployments | 1) Less effective testing 2) QAs consistance Fear of leaking defects & loosing confidence 3) QAs loose control on executions. Instead of methodical execution, QAs tend to fall in the gorilla testing to uncover hidden defects. Ask QAs how much % of time they involved in beyond-testcase testing, you'll get statistics. Human behavior. 4) Ask QAs on the confidence of coverages. | 1) Build requirement to testcases traceability. Use version information with sprint number, release number, date, delays etc all in headers. Mainatain versions. This was its easy to tap the complete and right information transfered to QAs. 2) Right traceability to Acceptance Criteria set by BA/PO. Take sign-off on this. Very very very imporrtance. 3) Any defects leaked to PROD, not part of these coverages, should be sent to Management for evaluations. Number of such defects metric shows leakges in this area. 4) Write testcases for every Prod Defect. Complete Bi-Directional traceability. 5) After every KT, use feedback survey to measure/track complete Knowledge is being transfered. 6) Track how many times QA has to go back to BA/Dev/PO for more doubts/enahnces/understandings/coverages. 7) Implement culture of reverse KT to PO/BA/Dev by QAs. V.V.V.Imp 8) QAs internal peer review to enhance coverages. 9) Share test readiness template with all coverage details before testing phase starts in 2nd week of the sprint. Mandatory to get green signal from DEV/PO/BA.
Metrics Dashboard for KT Evaluation Combine key metrics into a dashboard for tracking over time: Requirement-to-Test Case Coverage Ratio. Percentage of defects traced to KT issues. QA confidence rating post-KT (from surveys). Average follow-up questions per KT session. Number of gaps identified in test reviews due to insufficient KT.
Re-evaluate the backlog: |  |  | Test Case Coverage Metrics Formula: Coverage Percentage = (Number of Test Cases Written/ Number of Identified Scenarios)×100 Target 100% coverage for all identified scenarios, including edge and negative cases. Have mandatory minimum 100% coverages written on the number of scenarios given in acceptance criteria.
| Review the remaining work and prioritize tasks based on their value and complexity. | Use Requirement Decomposition: Identify workflows, user stories, and edge cases. Categorize complexity based on: Number of business rules. Number of input/output combinations. Dependencies on other features or systems. | Functional Complexity-Measurement Criteria: 1) Count the number of functional paths (primary and alternate). 2) Number of integrations and APIs involved. 3) UI elements or interactions required.
Communicate with stakeholders:
| Inform stakeholders about the potential delays and discuss options to adjust the scope or timeline. | Implement a culture of raising flags on delays. Document the cause and address delays from QAs. This will re-calibrate the sprint velocity.
Adjust sprint goals:
| If necessary, re-evaluate the sprint goal and adjust the work items to better fit the remaining time. | Implement QAs say in re-evaluating the feature development in sprints. Examples:
Improve estimation techniques:
| Focus on more accurate estimation methods to better predict the effort required for future work. | QAs should keep their past experience handy to giving story-points.
Address team issues:
| Identify and address any team dynamics or communication issues that may be hindering progress | Always enourage pair programming alike culture where dev depends on QA and vice versa. This will resolve many early defects, those gone pop in subsequent works, unhandled otherwise.

## In-Sprint Strategies
Sprint Strategy |  | Automation Strategy
Capacity | Sprint should not be more than 70% capacity. 30% buffer to start with, looing at the history of defect leakages
There will be two teams for any point of time
Planning | QAs should be part of finalizing the feature for release/sprint | 1st team will work on Automating Overall products Sanity checks [covering all scrum teams], Mini regression tests, individual component's health checks in isolation and bare minimal Integration checks | End user of this automation is in-sprint QAs. | 1stage: Cover Sanity for all scrum teams. 2nd stage: Cover individual features in isolation. 3rd stage: Cover integrated scenarios. 4th stage: Cover Regression E2E
Acceptance Criteria | QAs should get 100% coverage based KT from BA/PO/Dev | 2nd team will work on in-Sprint testing Plus in-sprint automation as much possible. Dont forcefully enter in automation as 1st team is already building automated validations. | 100% Manual testing. | Use KTs/Domain knowledge/Defect backlog and improve effectiveness of tests everyday. If time permits automate in-sprint new scenarios. Merge back to 1st teams code base.
Complusiry 3 amigos. Informal, continous and helping each others.
|  | 1st team will work on 100% automation. They will be provided with all necessary support from existing QA + Devs | 100% Automation
Sprint capacity - Complexity based scoring model for well balanced feature stories. | Incase of Any additional in-sprint work demands, example: unexpected defect fix & re-test 5 storypoint work, remove another least priority work of 5story point from sprint capacity. Dont burden QAs in in-sprint work. Otherwise effectiveness of testing reduced as testing window squeezed. | 1st team will create entire automation premise with all scenarios and test data in place
If Test Data is unavailable, ask existing functional tester to create some.
Try to use multi-thread as mush possible.
| Features selection should be well balanced. In imbalance features selection for a sprint, 1 feature developed well ahead than others, causes too many defects. Ask every QA to present their understanding in sprint planning, tell this to scrum master so that we can predictable system in place. If highly unbalanced, we can predict more defects, more resources need and more testing window required. | Build automation for CI/CD, build for devs/QAs/POs/BAs
Design all features in isolation, remove tight coupling. Use mocks/stubs with flags ON/OFF for integration. If not, atleast group mocks for inspinrt and integrated tests for UAT
1st team: BE API team, FE Web Team, Mobile team,
PS: https://clickup.com/blog/agile-prioritization-techniques/

## Feature Complexity Score Maturi
| Features | Priority | Completion | No Of sprints planned | No Of Releases it took [Main+point] | No of defects in PROD | Total No Of Defects in Pre-Prod | Defect Escape Rate
Priority Features | Feature 1 | 5 | 100% | 4 | 8 | 15 | 45 | 0.33333
| Feature 2 | 4 | 80% | 5 | 5 | 25 | 27 | 0.92593
| Feature 3 | 5 | 100%
| Feature 4 | 4 | 70%
| Feature 5 | 3 | 50%
| Feature 6 | 1 | 20%
| Feature 7 |  | 45%
| Feature 8 |  | 10%
| Feature 9 |  | 5%
| Feature 10 |  | 1%
Peripheral Features | Feature 11 |  | 0%
| Feature 12 |  | 0%
| Feature 13 |  | 0%
| Feature 14 |  | 0%
| Feature 15 |  | 0%
| Feature 16 |  | 0%
| Feature 17 |  | 0%
| Feature 18 |  | 0%